## Performance report
PROJECT PERFORMANCE ¦ REPORT
|  |  | Budget |  | Earned | Actual |  | Cost |  | Schedule |  | Performance Index |  | Forecast
| S# | Item description | Overall B.A.C. ($) | P.V. ($) | E.V. ($) | A.C. ($) | P.E.A. ($) | C.V. ($) | C.V. (%) | S.V. ($) | S.V. (%) | C.P.I. | S.P.I. | E.T.C. | E.A.C. | V.A.C. (%) | V.A.C. ($) | Average index | Status
| A | Program A | 489 | 254 | 225 | 266 |  | -41 | -16.14% | -29 | -11.42% | 0.84586 | 0.88583 | 312.1067 | 578.1067 | -18.22% | -89.1067 | 0.86585 | ORANGE
| A.1 | Project 1 | 186 | 93 | 90 | 100 |  | -10 | -10.75% | -3 | -3.226% | 0.9 | 0.96774 | 106.6667 | 206.6667 | -11.11% | -20.6667 | 0.93387 | ORANGE
| A.1.1 | Deliverable 1 | 100 | 55 | 50 | 60 |  | -10 | -18.18% | -5 | -9.091% | 0.83333 | 0.90909 | 60 | 120 | -20% | -20 | 0.87121 | ORANGE
| A.1.2 | Deliverable 2 | 28 | 13 | 14 | 18 |  | -4 | -30.77% | 1 | 7.692% | 0.77778 | 1.0769 | 18 | 36 | -28.57% | -8 | 0.92735 | ORANGE
| A.1.3 | Deliverable 3 | 58 | 25 | 26 | 22 |  | 4 | 16% | 1 | 4% | 1.1818 | 1.04 | 27.0769 | 49.0769 | 15.38% | 8.9231 | 1.1109 | GREEN
| A.2 | Project 2 | 303 | 161 | 135 | 166 |  | -31 | -19.25% | -26 | -16.15% | 0.81325 | 0.83851 | 206.5778 | 372.5778 | -22.96% | -69.5778 | 0.82588 | RED
| A.2.1 | Deliverable 1 | 180 | 92 | 80 | 100 |  | -20 | -21.74% | -12 | -13.04% | 0.8 | 0.86957 | 125 | 225 | -25% | -45 | 0.83478 | RED
| A.2.2 | Deliverable 2 | 45 | 35 | 20 | 30 |  | -10 | -28.57% | -15 | -42.86% | 0.66667 | 0.57143 | 37.5 | 67.5 | -50% | -22.5 | 0.61905 | BLACK
| A.2.3 | Deliverable 3 | 78 | 34 | 35 | 36 |  | -1 | -2.941% | 1 | 2.941% | 0.97222 | 1.0294 | 44.2286 | 80.2286 | -2.857% | -2.2286 | 1.0008 | GREEN
| B | Program B | 705 | 363 | 405 | 430 |  | -25 | -6.887% | 42 | 11.57% | 0.94186 | 1.1157 | 318.5185 | 748.5185 | -6.173% | -43.5185 | 1.0288 | GREEN
| B.1 | Project 1 | 375 | 148 | 210 | 225 |  | -15 | -10.14% | 62 | 41.89% | 0.93333 | 1.4189 | 176.7857 | 401.7857 | -7.143% | -26.7857 | 1.1761 | GREEN
| B.1.1 | Deliverable 1 | 250 | 55 | 125 | 150 |  | -25 | -45.45% | 70 | 127.3% | 0.83333 | 2.2727 | 150 | 300 | -20% | -50 | 1.553 | GREEN
| B.1.2 | Deliverable 2 | 100 | 82 | 70 | 65 |  | 5 | 6.098% | -12 | -14.63% | 1.0769 | 0.85366 | 27.8571 | 92.8571 | 7.143% | 7.1429 | 0.96529 | ORANGE
| B.1.3 | Deliverable 3 | 25 | 11 | 15 | 10 |  | 5 | 45.45% | 4 | 36.36% | 1.5 | 1.3636 | 6.6667 | 16.6667 | 33.33% | 8.3333 | 1.4318 | GREEN
| B.2 | Project 2 | 330 | 215 | 195 | 205 |  | -10 | -4.651% | -20 | -9.302% | 0.95122 | 0.90698 | 141.9231 | 346.9231 | -5.128% | -16.9231 | 0.9291 | ORANGE
| B.2.1 | Deliverable 1 | 90 | 55 | 60 | 50 |  | 10 | 18.18% | 5 | 9.091% | 1.2 | 1.0909 | 25 | 75 | 16.67% | 15 | 1.1455 | GREEN
| B.2.2 | Deliverable 2 | 90 | 60 | 50 | 45 |  | 5 | 8.333% | -10 | -16.67% | 1.1111 | 0.83333 | 36 | 81 | 10% | 9 | 0.97222 | ORANGE
| B.2.3 | Deliverable 3 | 150 | 100 | 85 | 110 |  | -25 | -25% | -15 | -15% | 0.77273 | 0.85 | 84.1176 | 194.1176 | -29.41% | -44.1176 | 0.81136 | RED
DEFINITIONS

## Definitions
PROJECT PERFORMANCE ¦ METRIC DEFINITIONS
S# | Metric | Abbrev. | Description | Formula/Value | Status | Description | Lower Value Limit
1 | Budget at Completion | B.A.C. | Baseline project cost |  | BLACK | Needs to be killed or restored | 0
2 | Actual Cost | A.C. | Total costs incurred in completing work during a given period |  | RED | Needs immediate attention | 0.65
3 | Earned Value | E.V. | Physical work completed during a given period |  | ORANGE | Slightly behind schedule/budget | 0.85
4 | Planned Value | P.V. | Physical work scheduled for completion during a given period |  | GREEN | On track | 1
5 | Cost Variance | C.V. | Cost overrun during a given period | E.V.-A.C.
6 | Cost Performance Index | C.P.I. | Cost efficiency ratio | E.V./A.C.
7 | Schedule Variance | S.V. | Schedule slipped during a given period | E.V.-P.V.
8 | Schedule Performance Index | S.P.I. | Schedule efficiency ratio | E.V./P.V.
9 | Estimate to Completion | E.T.C. | Expected additional cost needed | E.A.C.-A.C.
10 | Estimate at Completion | E.A.C. | Expected total cost | B.A.C./C.P.I.
11 | Variance at Completion | V.A.C. | Estimated cost overrun at end of project | B.A.C.-E.A.C.
12 | Status | n/a | Average of CPI and SPI | (C.P.I.+S.P.I.)/2
13 | Planned, Earned, Actual | P.E.A. | Planned, Earned & Actual along with Sparkline
REPORT